## Sheet1
Defect # | Status | Assigned to | Raised By | Version | Test Case ID | Step to Repoduce | Expected Result | Actual Result | Column1 | Status2 | Status3 | Link | Priority | Severity | Note
BUG-STAY-01 |  | Developer Testing Team | Ali |  | TC-STAY-01 | 1. Search Hotels 2. Scroll to bottom 3. The application enters an Infinite Loading State because the lazy-loading trigger fails to handle the 500 Internal Server Error (Database Connection Refused). The UI keeps trying to fetch data without a timeout or error boundary | Infinite results should load | SQL Error: Access denied for user 'root' | Infinite loading spinner and a SQL error appears in Console/Network. |  | #VALUE! | https://phptravels.net/stays/w/11-04-2026/12-04-2026/EG/1/1-0#171 | High | Critical
BUG-STAY-02 |  | Developer Testing Team | Ali |  | TC-STAY-02 | 1. Open Stays 2. Check any Amenity | Results should filter smoothly | JS Error: Cannot read property 'trim' of undefined |  |  | #VALUE! | https://phptravels.net/stays/cairo/11-04-2026/12-04-2026/EG/1/1-0 | Medium | Major
BUG-STAY-03 |  | Developer Testing Team | Ali |  | TC-STAY-03 | 1. Search for hotels in Cairo. 2. Change currency from USD to any other currency (e.g. EGP). |  | The system fails to perform currency conversion. Instead of converting the USD rates to the selected currency, the filtering logic treats the currency change as a 'Search Filter', leading to zero results. |  |  | #VALUE! | https://phptravels.net/stays/cairo/11-04-2026/12-04-2026/AF/1/1-0 | Medium | Major
BUG-STAY-04 |  | Developer Testing Team | Ali |  | TC-STAY-04 | 1. Send Search Request for Hotels. 2. Observe the API Response. |  | API intermittently returns SQL Error (Access Denied) instead of hotel results. It requires multiple retries to succeed. |  |  | #VALUE! |  | High | Critical | The backend is failing to authenticate with the database (user 'root'@'localhost').
BUG-STAY-05 |  | Developer Testing Team | Ali |  | TC-STAY-05 | Execute a search query for RateHawk module. | Should return a valid JSON response with hotel list or empty results. | SQL Error: Access denied for user 'root'@'localhost'. |  |  | #VALUE! | Request URL https://phptravels.net/modules/stays/ratehawk/search Request Method POST | High | Critical | Isolated Module Error: Database connection failed for this specific endpoint.
BUG-STAY-06 |  | Developer Testing Team | Ali |  | TC-STAY-06 | Execute a search query for Agoda/Hotels modules. | API should return available inventory for the selected destination. | Empty array [] is returned. |  |  | #VALUE! | Request URL https://phptravels.net/modules/stays/agoda/search Request Method POST | Medium | Major | Execute a search query for Agoda/Hotels modules.
BUG-STAY-07 |  | Developer Testing Team | Ali |  | TC-STAY-07 | Switch between different stay suppliers (Agoda, Travelport, RateHawk). | Seamless search experience with consistent data flow. | System dynamically changes the Endpoint per supplier. |  |  |  | Request URL https://phptravels.net/modules/stays/ratehawk/search Request Method POST Request URL https://phptravels.net/modules/stays/agoda/search Request Method POST Request URL https://phptravels.net/modules/stays/hotels/search Request Method POST Request URL https://phptravels.net/modules/stays/travelport/search Request Method POST Request URL https://phptravels.net/modules/stays/stuba/search Request Method POST | Low | Minor | Dynamic Endpoint Switching: Search behavior varies based on the active provider API.
BUG-STAY-08 |  | Developer Testing Team | Ali |  | TC-STAY-08 | Execute search for Hotelston module. | API should route the request to the correct supplier provider. | 404 Not Found: Endpoint not found. |  |  | #VALUE! |  | Medium | Major | The route for this specific supplier is missing or incorrectly mapped in the backend.
BUG-STAY-09 |  | Developer Testing Team | Ali |  | TC-STAY-09 | View property details or search results card. | Display list of amenities (e.g., Free Wi-Fi, Parking). | UI displays "undefinedundefinedundefined". |  |  | #VALUE! |  | Medium | Major | Data Mapping Issue: The Front-end is failing to read the amenities array from the API response.
BUG-STAY-10 |  | Developer Testing Team | Ali |  | TC-STAY-10 | Execute a search and check hotel images. | Real images of the hotels should be displayed. | Critical Data Gap: Missing essential hotel information for the end-user. |  |  | #VALUE! |  | High | Critical | The API integration fails to fetch or map actual image URLs.
BUG-STAY-11 |  | Developer Testing Team | Ali |  | TC-STAY-11 | Change website language to Arabic and search. | Hotel names and descriptions should be translated to Arabic. | Displays Placeholders (via.placeholder.com). |  |  | #VALUE! |  | High | Critical | The API request does not include the language parameter or the supplier doesn't support Arabic.
BUG-STAY-12 |  | Developer Testing Team | Ali |  | TC-STAY-12 | Inspect the JSON response for Amadeus. | Address and Amenities should be populated. | Data remains in English only. |  |  | #VALUE! |  | Medium | Major | Critical Data Gap: Missing essential hotel information for the end-user.
BUG-STAY-13 |  | Developer Testing Team | Ali |  | TC-STAY-13 | Switch language to Arabic and inspect the filter sidebar. | All labels and filter options should be fully translated into Arabic. | Mixed Languages: Some labels are Arabic (e.g. وسائل الراحة) while others are English (e.g. Free WiFi). |  |  | #VALUE! |  | Medium | Major | Hardcoded Strings: Many values are not linked to the translation files and appear in English by default.
BUG-STAY-14 |  | Developer Testing Team | Ali |  | TC-STAY-14 | Open Hotel Details page for Amadeus properties. | Display real hotel/room images and full address. | Static Placeholders for images and empty Address/Location fields. |  |  |  |  | High | Critical | The system is failing to fetch rich content (Media/Metadata) from the supplier.
BUG-STAY-15 |  | Developer Testing Team | Ali |  | TC-STAY-15 | Review Hotel Description section. | Show the actual description of the property. | Displays a Generic Template with missing data (e.g., "Located in ,"). |  |  |  |  | Medium | Minor | The UI is using hardcoded fallback text instead of dynamic API data.
BUG-STAY-16 |  | Developer Testing Team | Ali |  | TC-STAY-16 | Select a hotel, proceed to booking, and choose Stripe as payment method. | Stripe popup should appear and accept the test card (4242 4242 4242 4242) | Payment processed and redirected to "Booking Success". |  |  | #VALUE! |  |  |  | Ensure the currency in API (SAR/USD) matches Stripe's settings.
BUG-STAY-17 |  | Developer Testing Team | Ali |  | TC-STAY-17 | Use the Decline test card (4000 0000 0000 0002) | System should show a "Payment Declined" error message. (4000 0000 0000 0002) | Potential Bug: User redirected to success despite failure. |  |  | #VALUE! |  |  |  | Check if the API callback correctly handles failed transactions.
BUG-STAY-18 |  | Developer Testing Team | Ali |  | TC-PAY-DUP | 1. Book a room in Holiday Inn. 2. Complete payment via Stripe. 3. Immediately re-book the same room for the same date. | Room should be unavailable or show "Sold Out" after the first payment. | System allowed a second booking and accepted a second payment for the same room and date. |  |  | #VALUE! |  | High | Critical | Duplicate Invoices generated (CB3F239F & FE0ACAF8) for the same stay. This indicates a failure in real-time inventory synchronization.